## finalCopy
Tracking ID | MIS Period | PO No. | Tentative PO date | PO Description | TCU Code | Team Lead | Project Name | Rel / Non-Rel | Team Split | Account Codes | Technology | FS/CR | Item Name | FS/CR Name | Current Status | Challenge | General Remark | Patch | Assigned To | Total Effort( in Man-days) - Total effort of the project / deliverable | Effort in Man-days (for the month) | Effort Approval by | Effort Approval Date | Approval Status(Approved / Yet To Be Approved) | Request Received Date | Requested By (BSA) | Walkthough Planned date | Dev Planned Start date | Dev Planned End date | UAT Rel Planned date | Actual Walkthrough Date | Assigned for Development Date | Actual Dev Start Date | Actual Dev End date | UAT Promotion/Sent for Sign-off Date | Delayed Delivery | Reason of Delay | TS Document (Y-Prepared P-Pending N-Not required) | Reviewed By | Promotion Date | Promoted By | Promotion Ticket No. | MIS Group | Invoice No. | Final Status
JAVA0001 | Feb-18 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | Critical Illness Flat Extra and Rider 1 list for OTP2 | By Mail | Production |  |  | MLI | Saurabh Kumar | 11.00 | 11.00 | Mayank Gandhi | 12-Mar-18 | Approved | 26-Feb-18 | mayank gandhi | 26-Feb-18 | 26-Feb-18 | 12-Mar-18 | 13-Mar-18 | 26-Feb-18 | 26-Feb-18 | 26-Feb-18 | 12-Mar-18 | 13-Mar-18 |  |  | N | Rakesh | 14-Mar-18 | Mahima/Arvind | CR-947 | Java |  | Deleted Row
JAVA0002 | Feb-18 | 34085-8 |  |  |  | Rakesh Pawa | Welcome call | Non-Release | Java Team | Welcome call | Java | CR | Scheduling welcome call scheduler from 30 to 15 min | By Mail | Production |  |  | MLI | Ravi | 12.50 | 12.50 | Manish sachdeva | 19-Feb-18 | Approved | 31-Jan-18 | Sameer Sahay | 7-Feb-18 | 7-Feb-18 | 14-Feb-18 | 14-Feb-18 | 7-Feb-18 | 7-Feb-18 | 7-Feb-18 | 14-Feb-18 | 14-Feb-18 |  |  | N | Rakesh |  | Ravi/sapna |  | Java
JAVA0003 | Feb-18 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | OTP+ UIN Change Date logiv in ABPAPI | By Mail | Under Development |  |  | max | Saurabh Kumar | 2.00 | 2.00 | Mayank Gandhi | 15-Feb-18 | Approved | 14-Feb-18 | mayank gandhi | 14-Feb-18 | 19-Feb-18 | 19-Feb-18 | 19-Feb-18 | 14-Feb-18 | 19-Feb-18 | 21-Feb-18 | 22-Feb-18 | 23-Feb-18 |  |  | N | Rakesh | 14-Mar-18 | Mahima/Arvind | CR-947 | Java |  | Modified Row
JAVA0004 | Feb-18 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | OTP+ UIN Change Date logiv in ABPAPI | By Mail | Under Development |  |  | MLI | Saurabh Kumar | 2.00 | 2.00 | Mayank Gandhi | 15-Feb-18 | Approved | 14-Feb-18 | mayank gandhi | 14-Feb-18 | 19-Feb-18 | 19-Feb-18 | 19-Feb-18 | 14-Feb-18 | 19-Feb-18 | 21-Feb-18 | 22-Feb-18 | 23-Feb-18 |  |  | N | Rakesh | 14-Mar-18 | Mahima/Arvind | CR-947 | Java |  | Deleted Row
JAVA0005 | Feb-18 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | OTP+ UIN Change Date logiv in ABPAPI | By Mail | Under Development |  |  | MLI | Saurabh Kumar | 2.00 | 2.00 | Mayank Gandhi | 15-Feb-18 | Approved | 14-Feb-18 | mayank gandhi | 14-Feb-18 | 19-Feb-18 | 19-Feb-18 | 19-Feb-18 | 14-Feb-18 | 19-Feb-18 | 21-Feb-18 | 22-Feb-18 | 23-Feb-18 |  |  | N | Rakesh | 14-Mar-18 | Mahima/Arvind | CR-947 | Java |  | Deleted Row
JAVA0006 | Feb-18 | 27181-1 | [42 empty] | Created new Row
JAVA0007 | Feb-18 | 27181-1 | [42 empty] | Created new Row