## Sheet1
Tracking ID | MIS Period | PO No. | Tentative PO date | PO Description | TCU Code | Team Lead | Project Name | Rel / Non-Rel | Team Split | Account Codes | Technology | FS/CR | Item Name | FS/CR Name | Current Status | Challenge | General Remark | Patch | Assigned To | Total Effort ( in Man-days) - Total effort of the project / deliverable | Effort in Man-days (for the month) | Effort Approval by | Effort Approval Date | Approval Status (Approved / Yet To Be Approved) | Request Received Date | Requested By (BSA) | Walkthough Planned date | Dev Planned Start date | Dev Planned End date | UAT Rel Planned date | Actual Walkthrough Date | Assigned for Development Date | Actual Dev Start Date | Actual Dev End date | UAT Promotion/Sent for Sign-off Date | Delayed Delivery | Reason of Delay | TS Document (Y-Prepared P-Pending N-Not required) | Reviewed By | Promotion Date | Promoted By | Promotion Ticket No. | MIS Group | Invoice No.
JAVA0001 | 2018-02-01 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | Critical Illness Flat Extra and Rider 1 list for OTP2 | By Mail | Production |  |  | MLI | Saurabh Kumar | 11 | 11 | Mayank Gandhi | 2018-03-12 | Approved | 2018-02-26 | mayank gandhi | 2018-02-26 | 2018-02-26 | 2018-03-12 | 2018-03-13 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-12 | 2018-03-13 |  |  | N | Rakesh | 2018-03-14 | Mahima/Arvind | CR-947 | Java
JAVA0002 | 2018-02-01 | 34085-8 |  |  |  | Rakesh Pawa | Welcome call | Non-Release | Java Team | Welcome call | Java | CR | Scheduling welcome call scheduler from 30 to 15 min | By Mail | Production |  |  | MLI | Ravi | 12.5 | 12.5 | Manish sachdeva | 2018-02-19 | Approved | 2018-01-31 | Sameer Sahay | 2018-02-07 | 2018-02-07 | 2018-02-14 | 2018-02-14 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-14 | 2018-02-14 |  |  | N | Rakesh |  | Ravi/sapna |  | Java
JAVA0003 | 2018-02-01 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | OTP+ UIN Change Date logiv in ABPAPI | By Mail | Under Development |  |  | MLI | Saurabh Kumar | 2 | 2 | Mayank Gandhi | 2018-02-15 | Approved | 2018-02-14 | mayank gandhi | 2018-02-14 | 2018-02-19 | 2018-02-19 | 2018-02-19 | 2018-02-14 | 2018-02-19 | 2018-02-21 | 2018-02-22 | 2018-02-23 |  |  | N | Rakesh | 2018-03-14 | Mahima/Arvind | CR-947 | Java
JAVA0004 | 2018-02-01 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | OTP+ UIN Change Date logiv in ABPAPI | By Mail | Under Development |  |  | MLI | Saurabh Kumar | 2 | 2 | Mayank Gandhi | 2018-02-15 | Approved | 2018-02-14 | mayank gandhi | 2018-02-14 | 2018-02-19 | 2018-02-19 | 2018-02-19 | 2018-02-14 | 2018-02-19 | 2018-02-21 | 2018-02-22 | 2018-02-23 |  |  | N | Rakesh | 2018-03-14 | Mahima/Arvind | CR-947 | Java
JAVA0005 | 2018-02-01 | 27181-1 |  |  |  | Rakesh Pawa | IFTIS | Non-Release | Java Team | IFTIS | Java | CR | OTP+ UIN Change Date logiv in ABPAPI | By Mail | Under Development |  |  | MLI | Saurabh Kumar | 2 | 2 | Mayank Gandhi | 2018-02-15 | Approved | 2018-02-14 | mayank gandhi | 2018-02-14 | 2018-02-19 | 2018-02-19 | 2018-02-19 | 2018-02-14 | 2018-02-19 | 2018-02-21 | 2018-02-22 | 2018-02-23 |  |  | N | Rakesh | 2018-03-14 | Mahima/Arvind | CR-947 | Java